## Read Me
41 ZOY - Baseline master schedule (from MSP tracker 06-Oct-2026)
Source: ZOY - Baseline Master Schedule Tracker 06-OCT-2026.pdf. IDs are the MSP task IDs, so predecessors use them directly.
Dates, durations and predecessors are real. Start / Finish are also used as the baseline (the tracker holds one set of dates).
Progress and actual dates are SAMPLE data as at 12-Oct-2026, taken from the earlier tracker sheet (which tasks were started / finished and their % complete).
Predecessors: '12' = finish-to-start, '23SS+8d' = start-to-start with 8 days lag, '497FF+15d' = finish-to-finish, '+/-' lags are in working days.
Hidden rows: the PDF hides the children of collapsed tasks (for example the floor-wise blockwork). Links to hidden rows were re-pointed:
- 25 01 SLAB ( STILT FLOOR SLAB): predecessor 23SS+8d is a hidden sub-task of 14 (SUB- STRUCTURE); linked to 14 as SS+83d
- 40 03 SLAB ( PODIUM 2 FLOOR SLAB): predecessor 32FS-5d is a hidden sub-task of 26 (02 SLAB ( PODIUM 1 FLOOR SLAB)); linked to 26 as SS+75d
- 508 SANITARY FIXING: predecessor 461FS-20d is a hidden sub-task of 459 (PAINTING WORK); linked to 459 as SS+321d
- 510 VDP: predecessor 502FS+0d is a hidden sub-task of 459 (PAINTING WORK); linked to 459 as SS+407d
- 556 ACID WASH: predecessor 497FF+15d is a hidden sub-task of 459 (PAINTING WORK); linked to 459 as FF-14d
- 593 01 SLAB ( STILT FLOOR SLAB): predecessor 591SS+8d is a hidden sub-task of 582 (SUB- STRUCTURE); linked to 582 as SS+80d
- 1069 SANITARY FIXING: predecessor 1022FS-20d is a hidden sub-task of 1020 (PAINTING WORK); linked to 1020 as SS+323d
- 1071 VDP: predecessor 1063FF+10d is a hidden sub-task of 1020 (PAINTING WORK); linked to 1020 as FF+10d
- 1117 ACID WASH: predecessor 1058FF+15d is a hidden sub-task of 1020 (PAINTING WORK); linked to 1020 as FF-14d
- 1148 COMPOUND WALL: predecessor 1145FS+90d is a hidden sub-task of 1144 (STP); linked to 1144 as SS+246d
To get the full plan, export the MSP file with all outline levels expanded (or as XML) and import that instead.

## Schedule
ID | WBS | Level | Task Name | Wing / Area | Type | Duration (days) | Baseline Start | Baseline Finish | Start | Finish | Actual Start | Actual Finish | % Complete | Predecessors | Site Engineer
1 | 0 | 0 | 41 ZOY | Project | Summary | 1066.5 | 2025-07-01 | 2029-01-18 | 2025-07-01 | 2029-01-18 | 2025-07-01 |  | 6%
2 | 1 | 1 | SITE MOBILIZATION | Project | Task | 75 | 2025-07-01 | 2025-09-30 | 2025-07-01 | 2025-09-30 | 2025-07-01 | 2025-09-30 | 100%
10 | 2 | 1 | A-WING (B+Stilt+P1+P2+P3+P4+29F+Terrace) | A-Wing | Summary | 1057 | 2025-07-01 | 2029-01-06 | 2025-07-01 | 2029-01-06 | 2025-07-01 |  | 6% |  | Aditya Patil (Sr. Engineer)
11 | 2.1 | 2 | START OF CONSTRUCTION WORKS | A-Wing | Task | 1 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 100% |  | Aditya Patil (Sr. Engineer)
12 | 2.2 | 2 | EXCAVATION | A-Wing | Task | 113 | 2025-07-02 | 2025-11-19 | 2025-07-02 | 2025-11-19 | 2025-07-02 | 2025-11-19 | 100% | 11 | Aditya Patil (Sr. Engineer)
13 | 2.3 | 2 | RCC WORK | A-Wing | Summary | 728 | 2025-11-20 | 2028-04-20 | 2025-11-20 | 2028-04-20 | 2025-11-20 |  | 41% |  | Aditya Patil (Sr. Engineer)
14 | 2.3.1 | 3 | SUB- STRUCTURE | A-Wing | Task | 104 | 2025-11-20 | 2026-03-25 | 2025-11-20 | 2026-03-25 | 2025-11-20 | 2026-03-25 | 100% |  | Aditya Patil (Sr. Engineer)
24 | 2.3.2 | 3 | SUPER- STRUCTURE | A-Wing | Summary | 596 | 2026-02-25 | 2028-02-19 | 2026-02-25 | 2028-02-19 | 2026-02-25 |  | 31% |  | Aditya Patil (Sr. Engineer)
25 | 2.3.2.1 | 4 | 01 SLAB ( STILT FLOOR SLAB) | A-Wing | Task | 41 | 2026-02-25 | 2026-04-16 | 2026-02-25 | 2026-04-16 | 2026-02-25 | 2026-04-16 | 100% | 14SS+83d | Aditya Patil (Sr. Engineer)
26 | 2.3.2.2 | 4 | 02 SLAB ( PODIUM 1 FLOOR SLAB) | A-Wing | Task | 84 | 2026-04-06 | 2026-07-13 | 2026-04-06 | 2026-07-13 | 2026-04-06 | 2026-07-13 | 100% |  | Aditya Patil (Sr. Engineer)
33 | 2.3.2.3 | 4 | EXTENDED BASEMENT | A-Wing | Task | 163.8 | 2026-04-18 | 2026-11-02 | 2026-04-18 | 2026-11-02 | 2026-04-18 |  | 47% |  | Aditya Patil (Sr. Engineer)
40 | 2.3.2.4 | 4 | 03 SLAB ( PODIUM 2 FLOOR SLAB) | A-Wing | Task | 16.2 | 2026-07-02 | 2026-08-14 | 2026-07-02 | 2026-08-14 | 2026-07-02 | 2026-08-14 | 100% | 26SS+75d | Aditya Patil (Sr. Engineer)
41 | 2.3.2.5 | 4 | 04 SLAB ( PODIUM 3 FLOOR SLAB) | A-Wing | Task | 18 | 2026-08-09 | 2026-10-10 | 2026-08-09 | 2026-10-10 | 2026-08-09 |  | 80% | 40FS-5d | Aditya Patil (Sr. Engineer)
42 | 2.3.2.6 | 4 | 05 SLAB ( 1ST FLOOR) | A-Wing | Task | 20 | 2026-09-23 | 2026-10-30 | 2026-09-23 | 2026-10-30 | 2026-09-23 |  | 0% | 41FS-5d | Aditya Patil (Sr. Engineer)
43 | 2.3.2.7 | 4 | ADVANCE FOR ALUFORM | A-Wing | Task | 4 | 2026-05-25 | 2026-05-28 | 2026-05-25 | 2026-05-28 | 2026-05-25 | 2026-05-28 | 100% | 44FS-10d | Aditya Patil (Sr. Engineer)
44 | 2.3.2.8 | 4 | SHELL PLAN FINALIZATION | A-Wing | Milestone | 0 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 100% | 45FS-70d | Aditya Patil (Sr. Engineer)
45 | 2.3.2.9 | 4 | ALUFORM MATERIAL DELIVERY | A-Wing | Task | 1 | 2026-10-13 | 2026-10-13 | 2026-10-13 | 2026-10-13 |  |  | 0% | 46SS-10d | Aditya Patil (Sr. Engineer)
46 | 2.3.2.10 | 4 | 06 SLAB (2ND FLOOR ) - PART ALUFORM MOCK UP | A-Wing | Task | 35 | 2026-10-26 | 2026-12-08 | 2026-10-26 | 2026-12-08 |  |  | 0% | 42FS-5d | Aditya Patil (Sr. Engineer)
47 | 2.3.2.11 | 4 | 06 SLAB (2ND FLOOR ) - PART CONVENTIONAL | A-Wing | Task | 20 | 2026-10-31 | 2026-11-26 | 2026-10-31 | 2026-11-26 |  |  | 0% | 42 | Aditya Patil (Sr. Engineer)
48 | 2.3.2.12 | 4 | 07 SLAB (3RD FLOOR ) - COMPLETE ALUFORM MOCK UP | A-Wing | Task | 25 | 2026-11-27 | 2026-12-25 | 2026-11-27 | 2026-12-25 |  |  | 0% | 47 | Aditya Patil (Sr. Engineer)
49 | 2.3.2.13 | 4 | 09 SLAB (4TH FLOOR ) REFF. | A-Wing | Task | 20 | 2026-12-26 | 2027-01-18 | 2026-12-26 | 2027-01-18 |  |  | 0% | 48 | Aditya Patil (Sr. Engineer)
50 | 2.3.2.14 | 4 | 10 SLAB (5TH FLOOR ) | A-Wing | Task | 13 | 2027-01-19 | 2027-02-03 | 2027-01-19 | 2027-02-03 |  |  | 0% | 49 | Aditya Patil (Sr. Engineer)
51 | 2.3.2.15 | 4 | 11 SLAB (6TH FLOOR) | A-Wing | Task | 13 | 2027-02-04 | 2027-02-18 | 2027-02-04 | 2027-02-18 |  |  | 0% | 50 | Aditya Patil (Sr. Engineer)
52 | 2.3.2.16 | 4 | 12 SLAB (7TH FLOOR ) | A-Wing | Task | 12 | 2027-02-19 | 2027-03-04 | 2027-02-19 | 2027-03-04 |  |  | 0% | 51 | Aditya Patil (Sr. Engineer)
53 | 2.3.2.17 | 4 | 13 SLAB (8TH FLOOR ) | A-Wing | Task | 12 | 2027-03-05 | 2027-03-18 | 2027-03-05 | 2027-03-18 |  |  | 0% | 52 | Aditya Patil (Sr. Engineer)
54 | 2.3.2.18 | 4 | 14 SLAB (9TH FLOOR ) REFF. | A-Wing | Task | 12 | 2027-03-19 | 2027-04-03 | 2027-03-19 | 2027-04-03 |  |  | 0% | 53 | Aditya Patil (Sr. Engineer)
55 | 2.3.2.19 | 4 | 15 SLAB (10TH FLOOR) | A-Wing | Task | 12 | 2027-04-05 | 2027-04-19 | 2027-04-05 | 2027-04-19 |  |  | 0% | 54 | Aditya Patil (Sr. Engineer)
56 | 2.3.2.20 | 4 | 16 SLAB (11TH FLOOR ) | A-Wing | Task | 12 | 2027-04-20 | 2027-05-04 | 2027-04-20 | 2027-05-04 |  |  | 0% | 55 | Aditya Patil (Sr. Engineer)
57 | 2.3.2.21 | 4 | 17 SLAB (12TH FLOOR) | A-Wing | Task | 12 | 2027-05-05 | 2027-05-18 | 2027-05-05 | 2027-05-18 |  |  | 0% | 56 | Aditya Patil (Sr. Engineer)
58 | 2.3.2.22 | 4 | 18 SLAB (13TH FLOOR) | A-Wing | Task | 12 | 2027-05-19 | 2027-06-01 | 2027-05-19 | 2027-06-01 |  |  | 0% | 57 | Aditya Patil (Sr. Engineer)
59 | 2.3.2.23 | 4 | 19 SLAB (14TH FLOOR) REFF. | A-Wing | Task | 12 | 2027-06-02 | 2027-06-15 | 2027-06-02 | 2027-06-15 |  |  | 0% | 58 | Aditya Patil (Sr. Engineer)
60 | 2.3.2.24 | 4 | 20 SLAB (15TH FLOOR) | A-Wing | Task | 12 | 2027-06-16 | 2027-06-29 | 2027-06-16 | 2027-06-29 |  |  | 0% | 59 | Aditya Patil (Sr. Engineer)
61 | 2.3.2.25 | 4 | 21 SLAB (16TH FLOOR) | A-Wing | Task | 12 | 2027-06-30 | 2027-07-13 | 2027-06-30 | 2027-07-13 |  |  | 0% | 60 | Aditya Patil (Sr. Engineer)
62 | 2.3.2.26 | 4 | 22 SLAB (17TH FLOOR) | A-Wing | Task | 14 | 2027-07-14 | 2027-07-29 | 2027-07-14 | 2027-07-29 |  |  | 0% | 61 | Aditya Patil (Sr. Engineer)
63 | 2.3.2.27 | 4 | 23 SLAB (18TH FLOOR) (RCC Water Tank) | A-Wing | Task | 18 | 2027-07-30 | 2027-08-19 | 2027-07-30 | 2027-08-19 |  |  | 0% | 62 | Aditya Patil (Sr. Engineer)
64 | 2.3.2.28 | 4 | 24 SLAB (19TH FLOOR) REFF. | A-Wing | Task | 14 | 2027-08-20 | 2027-09-06 | 2027-08-20 | 2027-09-06 |  |  | 0% | 63 | Aditya Patil (Sr. Engineer)
65 | 2.3.2.29 | 4 | 25 SLAB (20TH FLOOR) | A-Wing | Task | 12 | 2027-09-07 | 2027-09-22 | 2027-09-07 | 2027-09-22 |  |  | 0% | 64 | Aditya Patil (Sr. Engineer)
66 | 2.3.2.30 | 4 | 26 SLAB (21ST FLOOR) | A-Wing | Task | 12 | 2027-09-23 | 2027-10-06 | 2027-09-23 | 2027-10-06 |  |  | 0% | 65 | Aditya Patil (Sr. Engineer)
67 | 2.3.2.31 | 4 | 27 SLAB (22ND FLOOR) | A-Wing | Task | 12 | 2027-10-07 | 2027-10-21 | 2027-10-07 | 2027-10-21 |  |  | 0% | 66 | Aditya Patil (Sr. Engineer)
68 | 2.3.2.32 | 4 | 28 SLAB(23RD FLOOR) | A-Wing | Task | 12 | 2027-10-22 | 2027-11-09 | 2027-10-22 | 2027-11-09 |  |  | 0% | 67 | Aditya Patil (Sr. Engineer)
69 | 2.3.2.33 | 4 | 29 SLAB(24TH FLOOR) REFF. | A-Wing | Task | 12 | 2027-11-10 | 2027-11-23 | 2027-11-10 | 2027-11-23 |  |  | 0% | 68 | Aditya Patil (Sr. Engineer)
70 | 2.3.2.34 | 4 | 30 SLAB(25TH FLOOR) | A-Wing | Task | 12 | 2027-11-24 | 2027-12-07 | 2027-11-24 | 2027-12-07 |  |  | 0% | 69 | Aditya Patil (Sr. Engineer)
71 | 2.3.2.35 | 4 | 31 SLAB(26TH FLOOR) | A-Wing | Task | 12 | 2027-12-08 | 2027-12-21 | 2027-12-08 | 2027-12-21 |  |  | 0% | 70 | Aditya Patil (Sr. Engineer)
72 | 2.3.2.36 | 4 | 32 SLAB(27TH FLOOR) | A-Wing | Task | 12 | 2027-12-22 | 2028-01-04 | 2027-12-22 | 2028-01-04 |  |  | 0% | 71 | Aditya Patil (Sr. Engineer)
73 | 2.3.2.37 | 4 | 33 SLAB(28TH FLOOR) | A-Wing | Task | 12 | 2028-01-05 | 2028-01-18 | 2028-01-05 | 2028-01-18 |  |  | 0% | 72 | Aditya Patil (Sr. Engineer)
74 | 2.3.2.38 | 4 | 34 SLAB(29TH FLOOR) | A-Wing | Task | 12 | 2028-01-19 | 2028-02-02 | 2028-01-19 | 2028-02-02 |  |  | 0% | 73 | Aditya Patil (Sr. Engineer)
75 | 2.3.2.39 | 4 | 35 SLAB (TERRACE FLOOR) | A-Wing | Task | 15 | 2028-02-03 | 2028-02-19 | 2028-02-03 | 2028-02-19 |  |  | 0% | 74 | Aditya Patil (Sr. Engineer)
76 | 2.3.3 | 3 | ABOVE TERRACE RCC | A-Wing | Task | 50 | 2028-02-21 | 2028-04-20 | 2028-02-21 | 2028-04-20 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
81 | 2.4 | 2 | BLOCKWORK | A-Wing | Task | 402 | 2027-01-19 | 2028-05-20 | 2027-01-19 | 2028-05-20 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
119 | 2.5 | 2 | INTERNAL PLASTER (GYPSUM) | A-Wing | Task | 349 | 2027-02-24 | 2028-04-22 | 2027-02-24 | 2028-04-22 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
155 | 2.6 | 2 | EXTERNAL GRINDING | A-Wing | Task | 318 | 2027-06-07 | 2028-06-24 | 2027-06-07 | 2028-06-24 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
167 | 2.7 | 2 | WATERPROOFING | A-Wing | Task | 808 | 2025-12-08 | 2028-08-10 | 2025-12-08 | 2028-08-10 | 2025-12-08 |  | 7% |  | Aditya Patil (Sr. Engineer)
207 | 2.8 | 2 | PLUMBING WORK | A-Wing | Task | 471 | 2027-02-25 | 2028-09-19 | 2027-02-25 | 2028-09-19 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
245 | 2.9 | 2 | TILING WORK | A-Wing | Task | 461 | 2027-04-13 | 2028-10-25 | 2027-04-13 | 2028-10-25 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
325 | 2.10 | 2 | CARPENTRY WORK | A-Wing | Task | 398 | 2027-07-20 | 2028-11-17 | 2027-07-20 | 2028-11-17 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
366 | 2.11 | 2 | FABRICATION | A-Wing | Task | 493 | 2027-04-20 | 2028-12-08 | 2027-04-20 | 2028-12-08 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
372 | 2.12 | 2 | ALUMINIUM WINDOWS | A-Wing | Task | 369 | 2027-08-11 | 2028-11-06 | 2027-08-11 | 2028-11-06 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
377 | 2.13 | 2 | ELECTRICAL WORK | A-Wing | Task | 846 | 2026-02-25 | 2028-12-20 | 2026-02-25 | 2028-12-20 | 2026-02-25 |  | 5% |  | Aditya Patil (Sr. Engineer)
459 | 2.14 | 2 | PAINTING WORK | A-Wing | Task | 387 | 2027-08-17 | 2028-12-02 | 2027-08-17 | 2028-12-02 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
505 | 2.15 | 2 | FALSE CEILING | A-Wing | Task | 60 | 2028-07-29 | 2028-10-12 | 2028-07-29 | 2028-10-12 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
508 | 2.16 | 2 | SANITARY FIXING | A-Wing | Task | 45 | 2028-08-26 | 2028-10-24 | 2028-08-26 | 2028-10-24 |  |  | 0% | 459SS+321d,556SS+15d | Aditya Patil (Sr. Engineer)
509 | 2.17 | 2 | CP | A-Wing | Task | 35 | 2028-11-23 | 2029-01-02 | 2028-11-23 | 2029-01-02 |  |  | 0% | 556FS+5d | Aditya Patil (Sr. Engineer)
510 | 2.18 | 2 | VDP | A-Wing | Task | 25 | 2028-12-04 | 2029-01-01 | 2028-12-04 | 2029-01-01 |  |  | 0% | 459SS+407d | Aditya Patil (Sr. Engineer)
511 | 2.19 | 2 | FIRE FIGHTING | A-Wing | Task | 484 | 2027-04-13 | 2028-11-21 | 2027-04-13 | 2028-11-21 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
550 | 2.20 | 2 | LIFT WORK | A-Wing | Task | 341 | 2027-07-14 | 2028-08-30 | 2027-07-14 | 2028-08-30 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
555 | 2.21 | 2 | SOLAR | A-Wing | Task | 60 | 2028-09-20 | 2028-12-02 | 2028-09-20 | 2028-12-02 |  |  | 0% | 207 | Aditya Patil (Sr. Engineer)
556 | 2.22 | 2 | ACID WASH | A-Wing | Task | 120 | 2028-06-21 | 2028-11-16 | 2028-06-21 | 2028-11-16 |  |  | 0% | 459FF-14d | Aditya Patil (Sr. Engineer)
557 | 2.23 | 2 | TILE GROUTING | A-Wing | Task | 100 | 2028-07-14 | 2028-11-16 | 2028-07-14 | 2028-11-16 |  |  | 0% | 556SS+20d | Aditya Patil (Sr. Engineer)
558 | 2.24 | 2 | SNAGGING & DESNAGGING | A-Wing | Task | 45 | 2028-10-19 | 2028-12-09 | 2028-10-19 | 2028-12-09 |  |  | 0% | 557FF+20d | Aditya Patil (Sr. Engineer)
559 | 2.25 | 2 | DEEP CLEANING | A-Wing | Task | 60 | 2028-09-28 | 2028-12-09 | 2028-09-28 | 2028-12-09 |  |  | 0% | 557FF+20d | Aditya Patil (Sr. Engineer)
560 | 2.26 | 2 | ELEVATION FEATURES | A-Wing | Task | 165 | 2028-05-22 | 2028-12-08 | 2028-05-22 | 2028-12-08 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
563 | 2.27 | 2 | OTHER SERVICE | A-Wing | Task | 15 | 2028-12-21 | 2029-01-06 | 2028-12-21 | 2029-01-06 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
574 | 2.28 | 2 | NOC'S | A-Wing | Task | 60 | 2028-10-30 | 2029-01-06 | 2028-10-30 | 2029-01-06 |  |  | 0% |  | Aditya Patil (Sr. Engineer)
578 | 3 | 1 | B-WING (B+Stilt+P1+P2+P3+P4+29F+Terrace) | B-Wing | Summary | 1050.6 | 2025-07-18 | 2029-01-17 | 2025-07-18 | 2029-01-17 | 2025-07-18 |  | 5% |  | Vicky Satpute (Sr. Engineer)
579 | 3.1 | 2 | START OF CONSTRUCTION WORKS | B-Wing | Task | 1 | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | 100% | 11FS+15d | Vicky Satpute (Sr. Engineer)
580 | 3.2 | 2 | EXCAVATION | B-Wing | Task | 90 | 2025-07-19 | 2025-11-10 | 2025-07-19 | 2025-11-10 | 2025-07-19 | 2025-11-10 | 100% | 579 | Vicky Satpute (Sr. Engineer)
581 | 3.3 | 2 | RCC WORK | B-Wing | Summary | 753.6 | 2025-11-11 | 2028-05-12 | 2025-11-11 | 2028-05-12 | 2025-11-11 |  | 37% |  | Vicky Satpute (Sr. Engineer)
582 | 3.3.1 | 3 | SUB- STRUCTURE | B-Wing | Task | 88 | 2025-11-11 | 2026-02-21 | 2025-11-11 | 2026-02-21 | 2025-11-11 | 2026-02-21 | 100% |  | Vicky Satpute (Sr. Engineer)
592 | 3.3.2 | 3 | SUPER- STRUCTURE | B-Wing | Summary | 624.6 | 2026-02-12 | 2028-03-13 | 2026-02-12 | 2028-03-13 | 2026-02-12 |  | 17% |  | Vicky Satpute (Sr. Engineer)
593 | 3.3.2.1 | 4 | 01 SLAB ( STILT FLOOR SLAB) | B-Wing | Task | 1 | 2026-02-12 | 2026-04-14 | 2026-02-12 | 2026-04-14 | 2026-02-12 | 2026-04-14 | 100% | 582SS+80d | Vicky Satpute (Sr. Engineer)
594 | 3.3.2.2 | 4 | 02 SLAB ( PODIUM 1 FLOOR SLAB) | B-Wing | Task | 61 | 2026-03-20 | 2026-05-30 | 2026-03-20 | 2026-05-30 | 2026-03-20 | 2026-05-30 | 100% |  | Vicky Satpute (Sr. Engineer)
601 | 3.3.2.3 | 4 | 03 SLAB ( PODIUM 2 FLOOR SLAB) | B-Wing | Task | 19.5 | 2026-05-30 | 2026-08-03 | 2026-05-30 | 2026-08-03 | 2026-05-30 | 2026-08-03 | 100% | 594 | Vicky Satpute (Sr. Engineer)
602 | 3.3.2.4 | 4 | 04 SLAB ( PODIUM 3 FLOOR SLAB) | B-Wing | Task | 18 | 2026-08-03 | 2026-11-03 | 2026-08-03 | 2026-11-03 | 2026-08-03 |  | 80% | 601FS-3d | Vicky Satpute (Sr. Engineer)
603 | 3.3.2.5 | 4 | 05 SLAB ( 1ST FLOOR) | B-Wing | Task | 20 | 2026-09-28 | 2026-11-24 | 2026-09-28 | 2026-11-24 | 2026-09-28 |  | 15% | 602FS-2d | Vicky Satpute (Sr. Engineer)
604 | 3.3.2.6 | 4 | ADVANCE FOR ALUFORM | B-Wing | Task | 4 | 2026-05-25 | 2026-05-28 | 2026-05-25 | 2026-05-28 | 2026-05-25 | 2026-05-28 | 100% | 605FS-10d | Vicky Satpute (Sr. Engineer)
605 | 3.3.2.7 | 4 | SHELL PLAN FINALIZATION | B-Wing | Milestone | 0 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 100% | 606FS-70d | Vicky Satpute (Sr. Engineer)
606 | 3.3.2.8 | 4 | ALUFORM MATERIAL DELIVERY | B-Wing | Task | 1 | 2026-11-03 | 2026-11-04 | 2026-11-03 | 2026-11-04 |  |  | 0% | 607SS-10d | Vicky Satpute (Sr. Engineer)
607 | 3.3.2.9 | 4 | 06 SLAB (2ND FLOOR ) - PART ALUFORM MOCK UP | B-Wing | Task | 35 | 2026-11-18 | 2026-12-29 | 2026-11-18 | 2026-12-29 |  |  | 0% | 603FS-5d | Vicky Satpute (Sr. Engineer)
608 | 3.3.2.10 | 4 | 06 SLAB (2ND FLOOR ) - PART CONVENTIONAL | B-Wing | Task | 20 | 2026-11-24 | 2026-12-17 | 2026-11-24 | 2026-12-17 |  |  | 0% | 603 | Vicky Satpute (Sr. Engineer)
609 | 3.3.2.11 | 4 | 07 SLAB (3RD FLOOR ) - COMPLETE ALUFORM MOCK UP | B-Wing | Task | 25 | 2026-12-17 | 2027-01-15 | 2026-12-17 | 2027-01-15 |  |  | 0% | 608 | Vicky Satpute (Sr. Engineer)
610 | 3.3.2.12 | 4 | 09 SLAB (4TH FLOOR ) REFF. | B-Wing | Task | 20 | 2027-01-15 | 2027-02-09 | 2027-01-15 | 2027-02-09 |  |  | 0% | 609 | Vicky Satpute (Sr. Engineer)
611 | 3.3.2.13 | 4 | 10 SLAB (5TH FLOOR ) | B-Wing | Task | 13 | 2027-02-09 | 2027-02-24 | 2027-02-09 | 2027-02-24 |  |  | 0% | 610 | Vicky Satpute (Sr. Engineer)
612 | 3.3.2.14 | 4 | 11 SLAB (6TH FLOOR) | B-Wing | Task | 13 | 2027-02-24 | 2027-03-11 | 2027-02-24 | 2027-03-11 |  |  | 0% | 611 | Vicky Satpute (Sr. Engineer)
613 | 3.3.2.15 | 4 | 12 SLAB (7TH FLOOR ) | B-Wing | Task | 12 | 2027-03-11 | 2027-03-27 | 2027-03-11 | 2027-03-27 |  |  | 0% | 612 | Vicky Satpute (Sr. Engineer)
614 | 3.3.2.16 | 4 | 13 SLAB (8TH FLOOR ) | B-Wing | Task | 12 | 2027-03-27 | 2027-04-12 | 2027-03-27 | 2027-04-12 |  |  | 0% | 613 | Vicky Satpute (Sr. Engineer)
615 | 3.3.2.17 | 4 | 14 SLAB (9TH FLOOR ) REFF. | B-Wing | Task | 12 | 2027-04-12 | 2027-04-26 | 2027-04-12 | 2027-04-26 |  |  | 0% | 614 | Vicky Satpute (Sr. Engineer)
616 | 3.3.2.18 | 4 | 15 SLAB (10TH FLOOR) | B-Wing | Task | 12 | 2027-04-26 | 2027-05-11 | 2027-04-26 | 2027-05-11 |  |  | 0% | 615 | Vicky Satpute (Sr. Engineer)
617 | 3.3.2.19 | 4 | 16 SLAB (11TH FLOOR ) | B-Wing | Task | 12 | 2027-05-11 | 2027-05-25 | 2027-05-11 | 2027-05-25 |  |  | 0% | 616 | Vicky Satpute (Sr. Engineer)
618 | 3.3.2.20 | 4 | 17 SLAB (12TH FLOOR) | B-Wing | Task | 12 | 2027-05-25 | 2027-06-08 | 2027-05-25 | 2027-06-08 |  |  | 0% | 617 | Vicky Satpute (Sr. Engineer)
619 | 3.3.2.21 | 4 | 18 SLAB (13TH FLOOR) | B-Wing | Task | 12 | 2027-06-08 | 2027-06-22 | 2027-06-08 | 2027-06-22 |  |  | 0% | 618 | Vicky Satpute (Sr. Engineer)
620 | 3.3.2.22 | 4 | 19 SLAB (14TH FLOOR) REFF. | B-Wing | Task | 12 | 2027-06-22 | 2027-07-06 | 2027-06-22 | 2027-07-06 |  |  | 0% | 619 | Vicky Satpute (Sr. Engineer)
621 | 3.3.2.23 | 4 | 20 SLAB (15TH FLOOR) | B-Wing | Task | 12 | 2027-07-06 | 2027-07-20 | 2027-07-06 | 2027-07-20 |  |  | 0% | 620 | Vicky Satpute (Sr. Engineer)
622 | 3.3.2.24 | 4 | 21 SLAB (16TH FLOOR) | B-Wing | Task | 12 | 2027-07-20 | 2027-08-03 | 2027-07-20 | 2027-08-03 |  |  | 0% | 621 | Vicky Satpute (Sr. Engineer)
623 | 3.3.2.25 | 4 | 22 SLAB (17TH FLOOR) | B-Wing | Task | 14 | 2027-08-03 | 2027-08-19 | 2027-08-03 | 2027-08-19 |  |  | 0% | 622 | Vicky Satpute (Sr. Engineer)
624 | 3.3.2.26 | 4 | 23 SLAB (18TH FLOOR) (RCC Water Tank) | B-Wing | Task | 18 | 2027-08-19 | 2027-09-10 | 2027-08-19 | 2027-09-10 |  |  | 0% | 623 | Vicky Satpute (Sr. Engineer)
625 | 3.3.2.27 | 4 | 24 SLAB (19TH FLOOR) REFF. | B-Wing | Task | 14 | 2027-09-10 | 2027-09-29 | 2027-09-10 | 2027-09-29 |  |  | 0% | 624 | Vicky Satpute (Sr. Engineer)
626 | 3.3.2.28 | 4 | 25 SLAB (20TH FLOOR) | B-Wing | Task | 12 | 2027-09-29 | 2027-10-14 | 2027-09-29 | 2027-10-14 |  |  | 0% | 625 | Vicky Satpute (Sr. Engineer)
627 | 3.3.2.29 | 4 | 26 SLAB (21ST FLOOR) | B-Wing | Task | 12 | 2027-10-14 | 2027-11-02 | 2027-10-14 | 2027-11-02 |  |  | 0% | 626 | Vicky Satpute (Sr. Engineer)
628 | 3.3.2.30 | 4 | 27 SLAB (22ND FLOOR) | B-Wing | Task | 12 | 2027-11-02 | 2027-11-16 | 2027-11-02 | 2027-11-16 |  |  | 0% | 627 | Vicky Satpute (Sr. Engineer)
629 | 3.3.2.31 | 4 | 28 SLAB(23RD FLOOR) | B-Wing | Task | 12 | 2027-11-16 | 2027-11-30 | 2027-11-16 | 2027-11-30 |  |  | 0% | 628 | Vicky Satpute (Sr. Engineer)
630 | 3.3.2.32 | 4 | 29 SLAB(24TH FLOOR) REFF. | B-Wing | Task | 12 | 2027-11-30 | 2027-12-14 | 2027-11-30 | 2027-12-14 |  |  | 0% | 629 | Vicky Satpute (Sr. Engineer)
631 | 3.3.2.33 | 4 | 30 SLAB(25TH FLOOR) | B-Wing | Task | 12 | 2027-12-14 | 2027-12-28 | 2027-12-14 | 2027-12-28 |  |  | 0% | 630 | Vicky Satpute (Sr. Engineer)
632 | 3.3.2.34 | 4 | 31 SLAB(26TH FLOOR) | B-Wing | Task | 12 | 2027-12-28 | 2028-01-11 | 2027-12-28 | 2028-01-11 |  |  | 0% | 631 | Vicky Satpute (Sr. Engineer)
633 | 3.3.2.35 | 4 | 32 SLAB(27TH FLOOR) | B-Wing | Task | 12 | 2028-01-11 | 2028-01-25 | 2028-01-11 | 2028-01-25 |  |  | 0% | 632 | Vicky Satpute (Sr. Engineer)
634 | 3.3.2.36 | 4 | 33 SLAB(28TH FLOOR) | B-Wing | Task | 12 | 2028-01-25 | 2028-02-09 | 2028-01-25 | 2028-02-09 |  |  | 0% | 633 | Vicky Satpute (Sr. Engineer)
635 | 3.3.2.37 | 4 | 34 SLAB(29TH FLOOR) | B-Wing | Task | 12 | 2028-02-09 | 2028-02-23 | 2028-02-09 | 2028-02-23 |  |  | 0% | 634 | Vicky Satpute (Sr. Engineer)
636 | 3.3.2.38 | 4 | 35 SLAB (TERRACE FLOOR) | B-Wing | Task | 15 | 2028-02-23 | 2028-03-13 | 2028-02-23 | 2028-03-13 |  |  | 0% | 635 | Vicky Satpute (Sr. Engineer)
637 | 3.3.3 | 3 | ABOVE TERRACE RCC | B-Wing | Task | 50 | 2028-03-13 | 2028-05-12 | 2028-03-13 | 2028-05-12 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
642 | 3.4 | 2 | BLOCKWORK | B-Wing | Task | 402 | 2027-02-09 | 2028-06-10 | 2027-02-09 | 2028-06-10 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
680 | 3.5 | 2 | INTERNAL PLASTER (GYPSUM) | B-Wing | Task | 349 | 2027-03-16 | 2028-05-15 | 2027-03-16 | 2028-05-15 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
716 | 3.6 | 2 | EXTERNAL GRINDING | B-Wing | Task | 318 | 2027-06-26 | 2028-07-15 | 2027-06-26 | 2028-07-15 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
728 | 3.7 | 2 | WATERPROOFING | B-Wing | Task | 833.6 | 2025-11-28 | 2028-09-04 | 2025-11-28 | 2028-09-04 | 2025-11-28 |  | 8% |  | Vicky Satpute (Sr. Engineer)
768 | 3.8 | 2 | PLUMBING WORK | B-Wing | Task | 471 | 2027-03-17 | 2028-10-11 | 2027-03-17 | 2028-10-11 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
806 | 3.9 | 2 | TILING WORK | B-Wing | Task | 461 | 2027-05-04 | 2028-11-15 | 2027-05-04 | 2028-11-15 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
886 | 3.10 | 2 | CARPENTRY WORK | B-Wing | Task | 398 | 2027-08-09 | 2028-12-08 | 2027-08-09 | 2028-12-08 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
927 | 3.11 | 2 | FABRICATION | B-Wing | Task | 493 | 2027-05-11 | 2028-12-29 | 2027-05-11 | 2028-12-29 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
933 | 3.12 | 2 | ALUMINIUM WINDOWS | B-Wing | Task | 369 | 2027-08-31 | 2028-11-27 | 2027-08-31 | 2028-11-27 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
938 | 3.13 | 2 | ELECTRICAL WORK | B-Wing | Task | 857.6 | 2026-03-04 | 2029-01-10 | 2026-03-04 | 2029-01-10 | 2026-03-04 |  | 2% |  | Vicky Satpute (Sr. Engineer)
1020 | 3.14 | 2 | PAINTING WORK | B-Wing | Task | 387 | 2027-09-07 | 2028-12-23 | 2027-09-07 | 2028-12-23 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
1066 | 3.15 | 2 | FALSE CEILING | B-Wing | Task | 60 | 2028-08-19 | 2028-11-06 | 2028-08-19 | 2028-11-06 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
1069 | 3.16 | 2 | SANITARY FIXING | B-Wing | Task | 45 | 2028-09-18 | 2028-11-14 | 2028-09-18 | 2028-11-14 |  |  | 0% | 1020SS+323d,1117SS+15d | Vicky Satpute (Sr. Engineer)
1070 | 3.17 | 2 | CP | B-Wing | Task | 45 | 2028-11-25 | 2029-01-17 | 2028-11-25 | 2029-01-17 |  |  | 0% | 1117FS-10d | Vicky Satpute (Sr. Engineer)
1071 | 3.18 | 2 | VDP | B-Wing | Task | 30 | 2028-11-30 | 2029-01-04 | 2028-11-30 | 2029-01-04 |  |  | 0% | 1020FF+10d | Vicky Satpute (Sr. Engineer)
1072 | 3.19 | 2 | FIRE FIGHTING | B-Wing | Task | 484 | 2027-05-04 | 2028-12-12 | 2027-05-04 | 2028-12-12 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
1111 | 3.20 | 2 | LIFT WORK | B-Wing | Task | 341 | 2027-08-03 | 2028-09-22 | 2027-08-03 | 2028-09-22 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
1116 | 3.21 | 2 | SOLAR | B-Wing | Task | 60 | 2028-10-11 | 2028-12-23 | 2028-10-11 | 2028-12-23 |  |  | 0% | 768 | Vicky Satpute (Sr. Engineer)
1117 | 3.22 | 2 | ACID WASH | B-Wing | Task | 120 | 2028-07-11 | 2028-12-07 | 2028-07-11 | 2028-12-07 |  |  | 0% | 1020FF-14d | Vicky Satpute (Sr. Engineer)
1118 | 3.23 | 2 | TILE GROUTING | B-Wing | Task | 100 | 2028-08-03 | 2028-12-07 | 2028-08-03 | 2028-12-07 |  |  | 0% | 1117SS+20d | Vicky Satpute (Sr. Engineer)
1119 | 3.24 | 2 | SNAGGING & DESNAGGING | B-Wing | Task | 40 | 2028-11-14 | 2028-12-30 | 2028-11-14 | 2028-12-30 |  |  | 0% | 1118FF+20d | Vicky Satpute (Sr. Engineer)
1120 | 3.25 | 2 | DEEP CLEANING | B-Wing | Task | 60 | 2028-10-21 | 2028-12-30 | 2028-10-21 | 2028-12-30 |  |  | 0% | 1118FF+20d | Vicky Satpute (Sr. Engineer)
1121 | 3.26 | 2 | ELEVATION FEATURES | B-Wing | Task | 165 | 2028-06-10 | 2028-12-29 | 2028-06-10 | 2028-12-29 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
1124 | 3.27 | 2 | OTHER SERVICE | B-Wing | Task | 15 | 2028-12-23 | 2029-01-10 | 2028-12-23 | 2029-01-10 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
1135 | 3.28 | 2 | NOC'S | B-Wing | Task | 44 | 2028-11-18 | 2029-01-09 | 2028-11-18 | 2029-01-09 |  |  | 0% |  | Vicky Satpute (Sr. Engineer)
1139 | 4 | 1 | EXTERNAL DEVELOPMENT WORK & SERVICES INCLUDING UTILITIES | External Development | Summary | 861.5 | 2026-03-10 | 2029-01-18 | 2026-03-10 | 2029-01-18 | 2026-03-10 |  | 4% |  | To be appointed (Jan-27)
1140 | 4.1 | 2 | UGWT | External Development | Summary | 681.5 | 2026-03-10 | 2028-06-13 | 2026-03-10 | 2028-06-13 | 2026-03-10 |  | 27% |  | To be appointed (Jan-27)
1141 | 4.1.1 | 3 | CIVIL WORKS | External Development | Task | 90 | 2026-03-10 | 2026-11-17 | 2026-03-10 | 2026-11-17 | 2026-03-10 |  | 65% | 25FS+5d | To be appointed (Jan-27)
1142 | 4.1.2 | 3 | ELECTRO- MECHANICAL WORKS | External Development | Task | 100 | 2028-01-14 | 2028-05-15 | 2028-01-14 | 2028-05-15 |  |  | 0% | 1141FS+350d | To be appointed (Jan-27)
1143 | 4.1.3 | 3 | TESTING& COMMISSIONING | External Development | Task | 25 | 2028-05-15 | 2028-06-13 | 2028-05-15 | 2028-06-13 |  |  | 0% | 1142 | To be appointed (Jan-27)
1144 | 4.2 | 2 | STP | External Development | Task | 545 | 2026-11-27 | 2028-09-15 | 2026-11-27 | 2028-09-15 |  |  | 0% |  | To be appointed (Jan-27)
1148 | 4.3 | 2 | COMPOUND WALL | External Development | Task | 250 | 2027-09-10 | 2028-07-10 | 2027-09-10 | 2028-07-10 |  |  | 0% | 1144SS+246d | To be appointed (Jan-27)
1149 | 4.4 | 2 | AMENITIES (Civil + Hardscape + Softscape) (Ground+Podium ) | External Development | Task | 180 | 2028-04-24 | 2028-11-29 | 2028-04-24 | 2028-11-29 |  |  | 0% | 119 | To be appointed (Jan-27)
1150 | 4.5 | 2 | PLUMBING & SEWERAGE WORKS | External Development | Task | 200 | 2028-05-09 | 2029-01-06 | 2028-05-09 | 2029-01-06 |  |  | 0% | 1143FS-30d | To be appointed (Jan-27)
1151 | 4.6 | 2 | TRANSFORMER ROOM/ SUB STATION/ EXTERNAL ELECTRICAL WORK | External Development | Task | 210 | 2028-05-09 | 2029-01-18 | 2028-05-09 | 2029-01-18 |  |  | 0% | 1143FS-30d | To be appointed (Jan-27)
1152 | 4.7 | 2 | ENTRANCE GATE WITH SECURITY CABIN & ENTRY GATE - 2 Nos | External Development | Task | 120 | 2028-07-11 | 2028-12-06 | 2028-07-11 | 2028-12-06 |  |  | 0% | 1148 | To be appointed (Jan-27)