## Read Me
41 ZOY - Sample Schedule (MVP template)
Purpose: template for the schedule upload. Keep these column names and the ID / Predecessors format.
How the dates were built (assumptions):
- The MSP export had masked dates (month only), so real dates were rebuilt: durations on a 6-day week (Sunday off).
- Slab cycles run one after another per wing; trades start as late as the project window allows, then follow their predecessors.
- 'Today' for actuals and % complete is 12-Oct-2026. No actual date is after today.
- Baseline dates are the hinted baseline months nearest the current start; they are an estimate, not the signed-off baseline.
- Summary rows (Type = Summary) take dates from their children. % Complete on summary rows is copied from the export.
- Predecessors use MSP style: '12' = finish-to-start, '14SS+30d' = start-to-start with 30 days lag. IDs are the ID column.
- Predecessor links are a proposed network (the export had none). The planner must confirm them before baselining.
- Site Engineer comes from the 41 ZOY organisation chart. External works engineer is not yet appointed.
Self-check on this file:
- Rows: 154 (145 work rows). Dependency violations: 0.
- Work rows whose rebuilt start month differs from the export's month: 35; finish month: 44.

## Schedule
ID | WBS | Level | Task Name | Wing / Area | Type | Duration (days) | Baseline Start | Baseline Finish | Start | Finish | Actual Start | Actual Finish | % Complete | Predecessors | Site Engineer
1 | 0 | 0 | 41 ZOY | Project | Summary | 1066.5 | 2025-07-01 | 2028-12-26 | 2025-07-01 | 2029-01-30 | 2025-07-01 |  | 6%
2 | 1 | 1 | SITE MOBILIZATION | Project | Task | 75 | 2025-07-01 | 2025-09-25 | 2025-07-01 | 2025-09-25 | 2025-07-01 | 2025-09-25 | 100%
3 | 2 | 1 | A-WING (B+Stilt+P1+P2+P3+P4+29F+Terrace) | A-Wing | Summary | 1057 | 2025-07-01 | 2028-11-30 | 2025-07-01 | 2029-01-27 | 2025-07-01 |  | 6% |  | Aditya Patil (Sr. Engineer)
4 | 2.1 | 2 | START OF CONSTRUCTION WORKS | A-Wing | Task | 1 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 100% | 2SS | Aditya Patil (Sr. Engineer)
5 | 2.2 | 2 | EXCAVATION | A-Wing | Task | 113 | 2025-07-01 | 2025-11-08 | 2025-07-01 | 2025-11-08 | 2025-07-01 | 2025-11-08 | 100% | 4SS | Aditya Patil (Sr. Engineer)
6 | 2.3 | 2 | RCC WORK | A-Wing | Summary | 728 | 2025-11-01 | 2028-03-20 | 2025-11-01 | 2028-04-29 | 2025-11-01 |  | 41% |  | Aditya Patil (Sr. Engineer)
7 | 2.3.1 | 3 | SUB- STRUCTURE | A-Wing | Task | 104 | 2025-11-01 | 2026-03-02 | 2025-11-01 | 2026-03-02 | 2025-11-01 | 2026-03-02 | 100% | 5SS+123d | Aditya Patil (Sr. Engineer)
8 | 2.3.2 | 3 | SUPER- STRUCTURE | A-Wing | Summary | 596 | 2026-02-23 | 2028-01-25 | 2026-03-03 | 2028-03-02 | 2026-03-03 |  | 31% |  | Aditya Patil (Sr. Engineer)
9 | 2.3.2.1 | 4 | 01 SLAB ( STILT FLOOR SLAB) | A-Wing | Task | 41 | 2026-02-23 | 2026-04-10 | 2026-03-03 | 2026-04-18 | 2026-03-03 | 2026-04-18 | 100% | 7 | Aditya Patil (Sr. Engineer)
10 | 2.3.2.2 | 4 | 02 SLAB ( PODIUM 1 FLOOR SLAB) | A-Wing | Task | 84 | 2026-04-22 | 2026-07-28 | 2026-04-20 | 2026-07-25 | 2026-04-20 | 2026-07-25 | 100% | 9 | Aditya Patil (Sr. Engineer)
11 | 2.3.2.3 | 4 | EXTENDED BASEMENT | A-Wing | Task | 163.8 | 2026-04-22 | 2026-10-29 | 2026-04-25 | 2026-11-02 | 2026-04-25 |  | 47% | 10SS+5d | Aditya Patil (Sr. Engineer)
12 | 2.3.2.4 | 4 | 03 SLAB ( PODIUM 2 FLOOR SLAB) | A-Wing | Task | 16.2 | 2026-05-22 | 2026-06-10 | 2026-07-27 | 2026-08-14 | 2026-07-27 | 2026-08-14 | 100% | 10 | Aditya Patil (Sr. Engineer)
13 | 2.3.2.5 | 4 | 04 SLAB ( PODIUM 3 FLOOR SLAB) | A-Wing | Task | 18 | 2026-06-22 | 2026-07-11 | 2026-08-15 | 2026-09-04 | 2026-08-15 |  | 80% | 12 | Aditya Patil (Sr. Engineer)
14 | 2.3.2.6 | 4 | 05 SLAB ( 1ST FLOOR) | A-Wing | Task | 20 | 2026-07-22 | 2026-08-13 | 2026-09-09 | 2026-10-01 | 2026-09-09 |  | 0% | 13FS+4d | Aditya Patil (Sr. Engineer)
15 | 2.3.2.7 | 4 | ADVANCE FOR ALUFORM | A-Wing | Task | 4 | 2026-05-01 | 2026-05-05 | 2026-05-01 | 2026-05-05 | 2026-05-01 | 2026-05-05 | 100% | 11SS+6d | Aditya Patil (Sr. Engineer)
16 | 2.3.2.8 | 4 | SHELL PLAN FINALIZATION | A-Wing | Milestone | 0 | 2026-02-23 | 2026-02-23 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 100% | 15FS+26d | Aditya Patil (Sr. Engineer)
17 | 2.3.2.9 | 4 | ALUFORM MATERIAL DELIVERY | A-Wing | Task | 1 | 2026-07-22 | 2026-07-22 | 2026-10-02 | 2026-10-02 |  |  | 0% | 14,16FS+122d | Aditya Patil (Sr. Engineer)
18 | 2.3.2.10 | 4 | 06 SLAB (2ND FLOOR ) - PART ALUFORM MOCK UP | A-Wing | Task | 35 | 2026-08-22 | 2026-10-01 | 2026-10-22 | 2026-12-01 |  |  | 0% | 17FS+19d | Aditya Patil (Sr. Engineer)
19 | 2.3.2.11 | 4 | 06 SLAB (2ND FLOOR ) - PART CONVENTIONAL | A-Wing | Task | 20 | 2026-08-22 | 2026-09-14 | 2026-12-02 | 2026-12-24 |  |  | 0% | 18 | Aditya Patil (Sr. Engineer)
20 | 2.3.2.12 | 4 | 07 SLAB (3RD FLOOR ) - COMPLETE ALUFORM MOCK UP | A-Wing | Task | 25 | 2026-09-22 | 2026-10-20 | 2026-12-25 | 2027-01-22 |  |  | 0% | 19 | Aditya Patil (Sr. Engineer)
21 | 2.3.2.13 | 4 | 09 SLAB (4TH FLOOR ) REFF. | A-Wing | Task | 20 | 2026-10-22 | 2026-11-13 | 2027-01-23 | 2027-02-15 |  |  | 0% | 20 | Aditya Patil (Sr. Engineer)
22 | 2.3.2.14 | 4 | 10 SLAB (5TH FLOOR ) | A-Wing | Task | 13 | 2026-11-23 | 2026-12-07 | 2027-02-16 | 2027-03-02 |  |  | 0% | 21 | Aditya Patil (Sr. Engineer)
23 | 2.3.2.15 | 4 | 11 SLAB (6TH FLOOR) | A-Wing | Task | 13 | 2026-12-15 | 2026-12-29 | 2027-03-03 | 2027-03-17 |  |  | 0% | 22 | Aditya Patil (Sr. Engineer)
24 | 2.3.2.16 | 4 | 12 SLAB (7TH FLOOR ) | A-Wing | Task | 12 | 2026-12-22 | 2027-01-04 | 2027-03-18 | 2027-03-31 |  |  | 0% | 23 | Aditya Patil (Sr. Engineer)
25 | 2.3.2.17 | 4 | 13 SLAB (8TH FLOOR ) | A-Wing | Task | 12 | 2027-01-15 | 2027-01-28 | 2027-04-01 | 2027-04-14 |  |  | 0% | 24 | Aditya Patil (Sr. Engineer)
26 | 2.3.2.18 | 4 | 14 SLAB (9TH FLOOR ) REFF. | A-Wing | Task | 12 | 2027-01-22 | 2027-02-04 | 2027-04-15 | 2027-04-28 |  |  | 0% | 25 | Aditya Patil (Sr. Engineer)
27 | 2.3.2.19 | 4 | 15 SLAB (10TH FLOOR) | A-Wing | Task | 12 | 2027-02-15 | 2027-02-27 | 2027-04-29 | 2027-05-12 |  |  | 0% | 26 | Aditya Patil (Sr. Engineer)
28 | 2.3.2.20 | 4 | 16 SLAB (11TH FLOOR ) | A-Wing | Task | 12 | 2027-02-22 | 2027-03-06 | 2027-05-13 | 2027-05-26 |  |  | 0% | 27 | Aditya Patil (Sr. Engineer)
29 | 2.3.2.21 | 4 | 17 SLAB (12TH FLOOR) | A-Wing | Task | 12 | 2027-03-15 | 2027-03-27 | 2027-05-27 | 2027-06-09 |  |  | 0% | 28 | Aditya Patil (Sr. Engineer)
30 | 2.3.2.22 | 4 | 18 SLAB (13TH FLOOR) | A-Wing | Task | 12 | 2027-03-22 | 2027-04-03 | 2027-06-10 | 2027-06-23 |  |  | 0% | 29 | Aditya Patil (Sr. Engineer)
31 | 2.3.2.23 | 4 | 19 SLAB (14TH FLOOR) REFF. | A-Wing | Task | 12 | 2027-04-15 | 2027-04-28 | 2027-06-24 | 2027-07-07 |  |  | 0% | 30 | Aditya Patil (Sr. Engineer)
32 | 2.3.2.24 | 4 | 20 SLAB (15TH FLOOR) | A-Wing | Task | 12 | 2027-04-22 | 2027-05-05 | 2027-07-08 | 2027-07-21 |  |  | 0% | 31 | Aditya Patil (Sr. Engineer)
33 | 2.3.2.25 | 4 | 21 SLAB (16TH FLOOR) | A-Wing | Task | 12 | 2027-05-15 | 2027-05-28 | 2027-07-22 | 2027-08-04 |  |  | 0% | 32 | Aditya Patil (Sr. Engineer)
34 | 2.3.2.26 | 4 | 22 SLAB (17TH FLOOR) | A-Wing | Task | 14 | 2027-05-22 | 2027-06-07 | 2027-08-05 | 2027-08-20 |  |  | 0% | 33 | Aditya Patil (Sr. Engineer)
35 | 2.3.2.27 | 4 | 23 SLAB (18TH FLOOR) (RCC Water Tank) | A-Wing | Task | 18 | 2027-06-22 | 2027-07-12 | 2027-08-21 | 2027-09-10 |  |  | 0% | 34 | Aditya Patil (Sr. Engineer)
36 | 2.3.2.28 | 4 | 24 SLAB (19TH FLOOR) REFF. | A-Wing | Task | 14 | 2027-07-15 | 2027-07-30 | 2027-09-11 | 2027-09-27 |  |  | 0% | 35 | Aditya Patil (Sr. Engineer)
37 | 2.3.2.29 | 4 | 25 SLAB (20TH FLOOR) | A-Wing | Task | 12 | 2027-07-22 | 2027-08-04 | 2027-09-28 | 2027-10-11 |  |  | 0% | 36 | Aditya Patil (Sr. Engineer)
38 | 2.3.2.30 | 4 | 26 SLAB (21ST FLOOR) | A-Wing | Task | 12 | 2027-08-16 | 2027-08-28 | 2027-10-12 | 2027-10-25 |  |  | 0% | 37 | Aditya Patil (Sr. Engineer)
39 | 2.3.2.31 | 4 | 27 SLAB (22ND FLOOR) | A-Wing | Task | 12 | 2027-08-23 | 2027-09-04 | 2027-10-26 | 2027-11-08 |  |  | 0% | 38 | Aditya Patil (Sr. Engineer)
40 | 2.3.2.32 | 4 | 28 SLAB(23RD FLOOR) | A-Wing | Task | 12 | 2027-09-15 | 2027-09-28 | 2027-11-09 | 2027-11-22 |  |  | 0% | 39 | Aditya Patil (Sr. Engineer)
41 | 2.3.2.33 | 4 | 29 SLAB(24TH FLOOR) REFF. | A-Wing | Task | 12 | 2027-09-22 | 2027-10-05 | 2027-11-23 | 2027-12-06 |  |  | 0% | 40 | Aditya Patil (Sr. Engineer)
42 | 2.3.2.34 | 4 | 30 SLAB(25TH FLOOR) | A-Wing | Task | 12 | 2027-10-22 | 2027-11-04 | 2027-12-07 | 2027-12-20 |  |  | 0% | 41 | Aditya Patil (Sr. Engineer)
43 | 2.3.2.35 | 4 | 31 SLAB(26TH FLOOR) | A-Wing | Task | 12 | 2027-11-15 | 2027-11-27 | 2027-12-21 | 2028-01-03 |  |  | 0% | 42 | Aditya Patil (Sr. Engineer)
44 | 2.3.2.36 | 4 | 32 SLAB(27TH FLOOR) | A-Wing | Task | 12 | 2027-11-22 | 2027-12-04 | 2028-01-04 | 2028-01-17 |  |  | 0% | 43 | Aditya Patil (Sr. Engineer)
45 | 2.3.2.37 | 4 | 33 SLAB(28TH FLOOR) | A-Wing | Task | 12 | 2027-12-15 | 2027-12-28 | 2028-01-18 | 2028-01-31 |  |  | 0% | 44 | Aditya Patil (Sr. Engineer)
46 | 2.3.2.38 | 4 | 34 SLAB(29TH FLOOR) | A-Wing | Task | 12 | 2027-12-22 | 2028-01-04 | 2028-02-01 | 2028-02-14 |  |  | 0% | 45 | Aditya Patil (Sr. Engineer)
47 | 2.3.2.39 | 4 | 35 SLAB (TERRACE FLOOR) | A-Wing | Task | 15 | 2028-01-08 | 2028-01-25 | 2028-02-15 | 2028-03-02 |  |  | 0% | 46 | Aditya Patil (Sr. Engineer)
48 | 2.3.3 | 3 | ABOVE TERRACE RCC | A-Wing | Task | 50 | 2028-01-22 | 2028-03-20 | 2028-03-03 | 2028-04-29 |  |  | 0% | 47 | Aditya Patil (Sr. Engineer)
49 | 2.4 | 2 | BLOCKWORK | A-Wing | Task | 402 | 2026-11-23 | 2028-03-04 | 2027-01-30 | 2028-05-12 |  |  | 0% | 21SS+7d | Aditya Patil (Sr. Engineer)
50 | 2.5 | 2 | INTERNAL PLASTER (GYPSUM) | A-Wing | Task | 349 | 2026-12-22 | 2028-02-01 | 2027-02-27 | 2028-04-08 |  |  | 0% | 49SS+28d | Aditya Patil (Sr. Engineer)
51 | 2.6 | 2 | EXTERNAL GRINDING | A-Wing | Task | 318 | 2027-04-22 | 2028-04-26 | 2027-06-26 | 2028-06-30 |  |  | 0% | 49SS+147d | Aditya Patil (Sr. Engineer)
52 | 2.7 | 2 | WATERPROOFING | A-Wing | Task | 808 | 2025-12-08 | 2028-07-06 | 2025-12-03 | 2028-07-01 | 2025-12-03 |  | 7% | 7SS+32d | Aditya Patil (Sr. Engineer)
53 | 2.8 | 2 | PLUMBING WORK | A-Wing | Task | 471 | 2026-12-22 | 2028-06-22 | 2027-02-27 | 2028-08-29 |  |  | 0% | 50SS | Aditya Patil (Sr. Engineer)
54 | 2.9 | 2 | TILING WORK | A-Wing | Task | 461 | 2027-02-22 | 2028-08-11 | 2027-04-30 | 2028-10-18 |  |  | 0% | 53SS+62d | Aditya Patil (Sr. Engineer)
55 | 2.10 | 2 | CARPENTRY WORK | A-Wing | Task | 398 | 2027-05-22 | 2028-08-28 | 2027-07-31 | 2028-11-06 |  |  | 0% | 50SS+154d | Aditya Patil (Sr. Engineer)
56 | 2.11 | 2 | FABRICATION | A-Wing | Task | 493 | 2027-02-22 | 2028-09-18 | 2027-04-30 | 2028-11-24 |  |  | 0% | 49SS+90d | Aditya Patil (Sr. Engineer)
57 | 2.12 | 2 | ALUMINIUM WINDOWS | A-Wing | Task | 369 | 2027-06-22 | 2028-08-24 | 2027-08-31 | 2028-11-02 |  |  | 0% | 49SS+213d | Aditya Patil (Sr. Engineer)
58 | 2.13 | 2 | ELECTRICAL WORK | A-Wing | Task | 846 | 2026-02-19 | 2028-11-01 | 2026-02-19 | 2028-11-01 | 2026-02-19 |  | 5% | 52SS+78d | Aditya Patil (Sr. Engineer)
59 | 2.14 | 2 | PAINTING WORK | A-Wing | Task | 387 | 2027-06-22 | 2028-09-14 | 2027-08-31 | 2028-11-23 |  |  | 0% | 57SS | Aditya Patil (Sr. Engineer)
60 | 2.15 | 2 | FALSE CEILING | A-Wing | Task | 60 | 2028-05-22 | 2028-07-29 | 2028-07-31 | 2028-10-07 |  |  | 0% | 54SS+458d | Aditya Patil (Sr. Engineer)
61 | 2.16 | 2 | SANITARY FIXING | A-Wing | Task | 45 | 2028-06-22 | 2028-08-12 | 2028-08-31 | 2028-10-21 |  |  | 0% | 54SS+489d | Aditya Patil (Sr. Engineer)
62 | 2.17 | 2 | CP | A-Wing | Task | 35 | 2028-09-22 | 2028-11-01 | 2028-11-30 | 2029-01-09 |  |  | 0% | 61FS+39d | Aditya Patil (Sr. Engineer)
63 | 2.18 | 2 | VDP | A-Wing | Task | 25 | 2028-10-23 | 2028-11-20 | 2028-12-30 | 2029-01-27 |  |  | 0% | 59FS+36d | Aditya Patil (Sr. Engineer)
64 | 2.19 | 2 | FIRE FIGHTING | A-Wing | Task | 484 | 2027-02-22 | 2028-09-07 | 2027-04-30 | 2028-11-14 |  |  | 0% | 50SS+62d | Aditya Patil (Sr. Engineer)
65 | 2.20 | 2 | LIFT WORK | A-Wing | Task | 341 | 2027-05-22 | 2028-06-22 | 2027-07-31 | 2028-08-31 |  |  | 0% | 49SS+182d | Aditya Patil (Sr. Engineer)
66 | 2.21 | 2 | SOLAR | A-Wing | Task | 60 | 2028-08-22 | 2028-10-30 | 2028-09-30 | 2028-12-08 |  |  | 0% | 59SS+396d | Aditya Patil (Sr. Engineer)
67 | 2.22 | 2 | ACID WASH | A-Wing | Task | 120 | 2028-04-22 | 2028-09-08 | 2028-06-30 | 2028-11-16 |  |  | 0% | 54SS+427d | Aditya Patil (Sr. Engineer)
68 | 2.23 | 2 | TILE GROUTING | A-Wing | Task | 100 | 2028-05-22 | 2028-09-14 | 2028-07-31 | 2028-11-23 |  |  | 0% | 67SS+31d | Aditya Patil (Sr. Engineer)
69 | 2.24 | 2 | SNAGGING & DESNAGGING | A-Wing | Task | 45 | 2028-09-22 | 2028-11-13 | 2028-10-31 | 2028-12-21 |  |  | 0% | 59SS+427d | Aditya Patil (Sr. Engineer)
70 | 2.25 | 2 | DEEP CLEANING | A-Wing | Task | 60 | 2028-09-22 | 2028-11-30 | 2028-09-30 | 2028-12-08 |  |  | 0% | 66SS | Aditya Patil (Sr. Engineer)
71 | 2.26 | 2 | ELEVATION FEATURES | A-Wing | Task | 165 | 2028-04-22 | 2028-10-31 | 2028-05-31 | 2028-12-08 |  |  | 0% | 51SS+340d | Aditya Patil (Sr. Engineer)
72 | 2.27 | 2 | OTHER SERVICE | A-Wing | Task | 15 | 2028-10-23 | 2028-11-08 | 2028-12-30 | 2029-01-16 |  |  | 0% | 69FS+8d | Aditya Patil (Sr. Engineer)
73 | 2.28 | 2 | NOC'S | A-Wing | Task | 60 | 2028-09-22 | 2028-11-30 | 2028-10-31 | 2029-01-08 |  |  | 0% | 69SS | Aditya Patil (Sr. Engineer)
74 | 3 | 1 | B-WING (B+Stilt+P1+P2+P3+P4+29F+Terrace) | B-Wing | Summary | 1050.6 | 2025-07-01 | 2028-12-26 | 2025-07-01 | 2029-01-20 | 2025-07-01 |  | 5% |  | Vicky Satpute (Sr. Engineer)
75 | 3.1 | 2 | START OF CONSTRUCTION WORKS | B-Wing | Task | 1 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 100% | 2SS | Vicky Satpute (Sr. Engineer)
76 | 3.2 | 2 | EXCAVATION | B-Wing | Task | 90 | 2025-07-22 | 2025-11-03 | 2025-07-21 | 2025-11-01 | 2025-07-21 | 2025-11-01 | 100% | 75FS+19d | Vicky Satpute (Sr. Engineer)
77 | 3.3 | 2 | RCC WORK | B-Wing | Summary | 753.6 | 2025-11-01 | 2028-03-20 | 2025-11-01 | 2028-05-11 | 2025-11-01 |  | 37% |  | Vicky Satpute (Sr. Engineer)
78 | 3.3.1 | 3 | SUB- STRUCTURE | B-Wing | Task | 88 | 2025-11-01 | 2026-02-11 | 2025-11-01 | 2026-02-11 | 2025-11-01 | 2026-02-11 | 100% | 76SS+103d | Vicky Satpute (Sr. Engineer)
79 | 3.3.2 | 3 | SUPER- STRUCTURE | B-Wing | Summary | 624.6 | 2026-02-09 | 2028-01-07 | 2026-02-12 | 2028-03-14 | 2026-02-12 |  | 17% |  | Vicky Satpute (Sr. Engineer)
80 | 3.3.2.1 | 4 | 01 SLAB ( STILT FLOOR SLAB) | B-Wing | Task | 1 | 2026-02-09 | 2026-02-09 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 100% | 78 | Vicky Satpute (Sr. Engineer)
81 | 3.3.2.2 | 4 | 02 SLAB ( PODIUM 1 FLOOR SLAB) | B-Wing | Task | 61 | 2026-04-01 | 2026-06-10 | 2026-03-02 | 2026-05-11 | 2026-03-02 | 2026-05-11 | 100% | 80FS+17d | Vicky Satpute (Sr. Engineer)
82 | 3.3.2.3 | 4 | 03 SLAB ( PODIUM 2 FLOOR SLAB) | B-Wing | Task | 19.5 | 2026-05-15 | 2026-06-06 | 2026-05-12 | 2026-06-03 | 2026-05-12 | 2026-06-03 | 100% | 81 | Vicky Satpute (Sr. Engineer)
83 | 3.3.2.4 | 4 | 04 SLAB ( PODIUM 3 FLOOR SLAB) | B-Wing | Task | 18 | 2026-06-08 | 2026-06-27 | 2026-08-12 | 2026-09-01 | 2026-08-12 |  | 80% | 82FS+69d | Vicky Satpute (Sr. Engineer)
84 | 3.3.2.5 | 4 | 05 SLAB ( 1ST FLOOR) | B-Wing | Task | 20 | 2026-07-22 | 2026-08-13 | 2026-09-09 | 2026-10-01 | 2026-09-09 |  | 15% | 83FS+7d | Vicky Satpute (Sr. Engineer)
85 | 3.3.2.6 | 4 | ADVANCE FOR ALUFORM | B-Wing | Task | 4 | 2026-05-01 | 2026-05-05 | 2026-05-01 | 2026-05-05 | 2026-05-01 | 2026-05-05 | 100% | 128SS+55d | Vicky Satpute (Sr. Engineer)
86 | 3.3.2.7 | 4 | SHELL PLAN FINALIZATION | B-Wing | Milestone | 0 | 2026-02-23 | 2026-02-23 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 100% | 85FS+26d | Vicky Satpute (Sr. Engineer)
87 | 3.3.2.8 | 4 | ALUFORM MATERIAL DELIVERY | B-Wing | Task | 1 | 2026-07-22 | 2026-07-22 | 2026-11-02 | 2026-11-02 |  |  | 0% | 84FS+31d,86FS+153d | Vicky Satpute (Sr. Engineer)
88 | 3.3.2.9 | 4 | 06 SLAB (2ND FLOOR ) - PART ALUFORM MOCK UP | B-Wing | Task | 35 | 2026-08-22 | 2026-10-01 | 2026-11-03 | 2026-12-12 |  |  | 0% | 87 | Vicky Satpute (Sr. Engineer)
89 | 3.3.2.10 | 4 | 06 SLAB (2ND FLOOR ) - PART CONVENTIONAL | B-Wing | Task | 20 | 2026-08-22 | 2026-09-14 | 2026-12-14 | 2027-01-05 |  |  | 0% | 88 | Vicky Satpute (Sr. Engineer)
90 | 3.3.2.11 | 4 | 07 SLAB (3RD FLOOR ) - COMPLETE ALUFORM MOCK UP | B-Wing | Task | 25 | 2026-09-22 | 2026-10-20 | 2027-01-06 | 2027-02-03 |  |  | 0% | 89 | Vicky Satpute (Sr. Engineer)
91 | 3.3.2.12 | 4 | 09 SLAB (4TH FLOOR ) REFF. | B-Wing | Task | 20 | 2026-10-22 | 2026-11-13 | 2027-02-04 | 2027-02-26 |  |  | 0% | 90 | Vicky Satpute (Sr. Engineer)
92 | 3.3.2.13 | 4 | 10 SLAB (5TH FLOOR ) | B-Wing | Task | 13 | 2026-11-16 | 2026-11-30 | 2027-02-27 | 2027-03-13 |  |  | 0% | 91 | Vicky Satpute (Sr. Engineer)
93 | 3.3.2.14 | 4 | 11 SLAB (6TH FLOOR) | B-Wing | Task | 13 | 2026-11-23 | 2026-12-07 | 2027-03-15 | 2027-03-29 |  |  | 0% | 92 | Vicky Satpute (Sr. Engineer)
94 | 3.3.2.15 | 4 | 12 SLAB (7TH FLOOR ) | B-Wing | Task | 12 | 2026-12-15 | 2026-12-28 | 2027-03-30 | 2027-04-12 |  |  | 0% | 93 | Vicky Satpute (Sr. Engineer)
95 | 3.3.2.16 | 4 | 13 SLAB (8TH FLOOR ) | B-Wing | Task | 12 | 2026-12-22 | 2027-01-04 | 2027-04-13 | 2027-04-26 |  |  | 0% | 94 | Vicky Satpute (Sr. Engineer)
96 | 3.3.2.17 | 4 | 14 SLAB (9TH FLOOR ) REFF. | B-Wing | Task | 12 | 2027-01-15 | 2027-01-28 | 2027-04-27 | 2027-05-10 |  |  | 0% | 95 | Vicky Satpute (Sr. Engineer)
97 | 3.3.2.18 | 4 | 15 SLAB (10TH FLOOR) | B-Wing | Task | 12 | 2027-01-22 | 2027-02-04 | 2027-05-11 | 2027-05-24 |  |  | 0% | 96 | Vicky Satpute (Sr. Engineer)
98 | 3.3.2.19 | 4 | 16 SLAB (11TH FLOOR ) | B-Wing | Task | 12 | 2027-02-15 | 2027-02-27 | 2027-05-25 | 2027-06-07 |  |  | 0% | 97 | Vicky Satpute (Sr. Engineer)
99 | 3.3.2.20 | 4 | 17 SLAB (12TH FLOOR) | B-Wing | Task | 12 | 2027-02-22 | 2027-03-06 | 2027-06-08 | 2027-06-21 |  |  | 0% | 98 | Vicky Satpute (Sr. Engineer)
100 | 3.3.2.21 | 4 | 18 SLAB (13TH FLOOR) | B-Wing | Task | 12 | 2027-03-15 | 2027-03-27 | 2027-06-22 | 2027-07-05 |  |  | 0% | 99 | Vicky Satpute (Sr. Engineer)
101 | 3.3.2.22 | 4 | 19 SLAB (14TH FLOOR) REFF. | B-Wing | Task | 12 | 2027-03-22 | 2027-04-03 | 2027-07-06 | 2027-07-19 |  |  | 0% | 100 | Vicky Satpute (Sr. Engineer)
102 | 3.3.2.23 | 4 | 20 SLAB (15TH FLOOR) | B-Wing | Task | 12 | 2027-04-22 | 2027-05-05 | 2027-07-20 | 2027-08-02 |  |  | 0% | 101 | Vicky Satpute (Sr. Engineer)
103 | 3.3.2.24 | 4 | 21 SLAB (16TH FLOOR) | B-Wing | Task | 12 | 2027-05-15 | 2027-05-28 | 2027-08-03 | 2027-08-16 |  |  | 0% | 102 | Vicky Satpute (Sr. Engineer)
104 | 3.3.2.25 | 4 | 22 SLAB (17TH FLOOR) | B-Wing | Task | 14 | 2027-05-22 | 2027-06-07 | 2027-08-17 | 2027-09-01 |  |  | 0% | 103 | Vicky Satpute (Sr. Engineer)
105 | 3.3.2.26 | 4 | 23 SLAB (18TH FLOOR) (RCC Water Tank) | B-Wing | Task | 18 | 2027-06-08 | 2027-06-28 | 2027-09-02 | 2027-09-22 |  |  | 0% | 104 | Vicky Satpute (Sr. Engineer)
106 | 3.3.2.27 | 4 | 24 SLAB (19TH FLOOR) REFF. | B-Wing | Task | 14 | 2027-06-22 | 2027-07-07 | 2027-09-23 | 2027-10-08 |  |  | 0% | 105 | Vicky Satpute (Sr. Engineer)
107 | 3.3.2.28 | 4 | 25 SLAB (20TH FLOOR) | B-Wing | Task | 12 | 2027-07-15 | 2027-07-28 | 2027-10-09 | 2027-10-22 |  |  | 0% | 106 | Vicky Satpute (Sr. Engineer)
108 | 3.3.2.29 | 4 | 26 SLAB (21ST FLOOR) | B-Wing | Task | 12 | 2027-07-22 | 2027-08-04 | 2027-10-23 | 2027-11-05 |  |  | 0% | 107 | Vicky Satpute (Sr. Engineer)
109 | 3.3.2.30 | 4 | 27 SLAB (22ND FLOOR) | B-Wing | Task | 12 | 2027-08-16 | 2027-08-28 | 2027-11-06 | 2027-11-19 |  |  | 0% | 108 | Vicky Satpute (Sr. Engineer)
110 | 3.3.2.31 | 4 | 28 SLAB(23RD FLOOR) | B-Wing | Task | 12 | 2027-08-23 | 2027-09-04 | 2027-11-20 | 2027-12-03 |  |  | 0% | 109 | Vicky Satpute (Sr. Engineer)
111 | 3.3.2.32 | 4 | 29 SLAB(24TH FLOOR) REFF. | B-Wing | Task | 12 | 2027-09-22 | 2027-10-05 | 2027-12-04 | 2027-12-17 |  |  | 0% | 110 | Vicky Satpute (Sr. Engineer)
112 | 3.3.2.33 | 4 | 30 SLAB(25TH FLOOR) | B-Wing | Task | 12 | 2027-10-15 | 2027-10-28 | 2027-12-18 | 2027-12-31 |  |  | 0% | 111 | Vicky Satpute (Sr. Engineer)
113 | 3.3.2.34 | 4 | 31 SLAB(26TH FLOOR) | B-Wing | Task | 12 | 2027-10-22 | 2027-11-04 | 2028-01-01 | 2028-01-14 |  |  | 0% | 112 | Vicky Satpute (Sr. Engineer)
114 | 3.3.2.35 | 4 | 32 SLAB(27TH FLOOR) | B-Wing | Task | 12 | 2027-11-15 | 2027-11-27 | 2028-01-15 | 2028-01-28 |  |  | 0% | 113 | Vicky Satpute (Sr. Engineer)
115 | 3.3.2.36 | 4 | 33 SLAB(28TH FLOOR) | B-Wing | Task | 12 | 2027-11-22 | 2027-12-04 | 2028-01-29 | 2028-02-11 |  |  | 0% | 114 | Vicky Satpute (Sr. Engineer)
116 | 3.3.2.37 | 4 | 34 SLAB(29TH FLOOR) | B-Wing | Task | 12 | 2027-12-15 | 2027-12-28 | 2028-02-12 | 2028-02-25 |  |  | 0% | 115 | Vicky Satpute (Sr. Engineer)
117 | 3.3.2.38 | 4 | 35 SLAB (TERRACE FLOOR) | B-Wing | Task | 15 | 2027-12-22 | 2028-01-07 | 2028-02-26 | 2028-03-14 |  |  | 0% | 116 | Vicky Satpute (Sr. Engineer)
118 | 3.3.3 | 3 | ABOVE TERRACE RCC | B-Wing | Task | 50 | 2028-01-22 | 2028-03-20 | 2028-03-15 | 2028-05-11 |  |  | 0% | 117 | Vicky Satpute (Sr. Engineer)
119 | 3.4 | 2 | BLOCKWORK | B-Wing | Task | 402 | 2026-11-23 | 2028-03-04 | 2027-02-27 | 2028-06-09 |  |  | 0% | 92SS | Vicky Satpute (Sr. Engineer)
120 | 3.5 | 2 | INTERNAL PLASTER (GYPSUM) | B-Wing | Task | 349 | 2026-12-22 | 2028-02-01 | 2027-03-31 | 2028-05-10 |  |  | 0% | 119SS+32d | Vicky Satpute (Sr. Engineer)
121 | 3.6 | 2 | EXTERNAL GRINDING | B-Wing | Task | 318 | 2027-04-22 | 2028-04-26 | 2027-06-30 | 2028-07-04 |  |  | 0% | 119SS+123d | Vicky Satpute (Sr. Engineer)
122 | 3.7 | 2 | WATERPROOFING | B-Wing | Task | 833.6 | 2025-11-08 | 2028-07-07 | 2025-11-03 | 2028-07-01 | 2025-11-03 |  | 8% | 78SS+2d | Vicky Satpute (Sr. Engineer)
123 | 3.8 | 2 | PLUMBING WORK | B-Wing | Task | 471 | 2026-12-22 | 2028-06-22 | 2027-03-31 | 2028-09-29 |  |  | 0% | 120SS | Vicky Satpute (Sr. Engineer)
124 | 3.9 | 2 | TILING WORK | B-Wing | Task | 461 | 2027-01-22 | 2028-07-12 | 2027-05-31 | 2028-11-17 |  |  | 0% | 123SS+61d | Vicky Satpute (Sr. Engineer)
125 | 3.10 | 2 | CARPENTRY WORK | B-Wing | Task | 398 | 2027-05-22 | 2028-08-28 | 2027-08-31 | 2028-12-06 |  |  | 0% | 120SS+153d | Vicky Satpute (Sr. Engineer)
126 | 3.11 | 2 | FABRICATION | B-Wing | Task | 493 | 2027-02-22 | 2028-09-18 | 2027-05-31 | 2028-12-25 |  |  | 0% | 119SS+93d | Vicky Satpute (Sr. Engineer)
127 | 3.12 | 2 | ALUMINIUM WINDOWS | B-Wing | Task | 369 | 2027-06-22 | 2028-08-24 | 2027-08-31 | 2028-11-02 |  |  | 0% | 119SS+185d | Vicky Satpute (Sr. Engineer)
128 | 3.13 | 2 | ELECTRICAL WORK | B-Wing | Task | 857.6 | 2026-04-01 | 2028-12-26 | 2026-03-07 | 2028-12-01 | 2026-03-07 |  | 2% | 81SS+5d | Vicky Satpute (Sr. Engineer)
129 | 3.14 | 2 | PAINTING WORK | B-Wing | Task | 387 | 2027-06-22 | 2028-09-14 | 2027-09-30 | 2028-12-23 |  |  | 0% | 106SS+7d | Vicky Satpute (Sr. Engineer)
130 | 3.15 | 2 | FALSE CEILING | B-Wing | Task | 60 | 2028-05-22 | 2028-07-29 | 2028-08-31 | 2028-11-08 |  |  | 0% | 124SS+458d | Vicky Satpute (Sr. Engineer)
131 | 3.16 | 2 | SANITARY FIXING | B-Wing | Task | 45 | 2028-06-22 | 2028-08-12 | 2028-09-30 | 2028-11-21 |  |  | 0% | 124SS+488d | Vicky Satpute (Sr. Engineer)
132 | 3.17 | 2 | CP | B-Wing | Task | 45 | 2028-09-22 | 2028-11-13 | 2028-11-30 | 2029-01-20 |  |  | 0% | 131FS+8d | Vicky Satpute (Sr. Engineer)
133 | 3.18 | 2 | VDP | B-Wing | Task | 30 | 2028-09-22 | 2028-10-26 | 2028-11-30 | 2029-01-03 |  |  | 0% | 129SS+427d | Vicky Satpute (Sr. Engineer)
134 | 3.19 | 2 | FIRE FIGHTING | B-Wing | Task | 484 | 2027-01-22 | 2028-08-08 | 2027-05-31 | 2028-12-14 |  |  | 0% | 120SS+61d | Vicky Satpute (Sr. Engineer)
135 | 3.20 | 2 | LIFT WORK | B-Wing | Task | 341 | 2027-05-22 | 2028-06-22 | 2027-08-31 | 2028-09-30 |  |  | 0% | 119SS+185d | Vicky Satpute (Sr. Engineer)
136 | 3.21 | 2 | SOLAR | B-Wing | Task | 60 | 2028-08-22 | 2028-10-30 | 2028-10-23 | 2028-12-30 |  |  | 0% | 129SS+389d | Vicky Satpute (Sr. Engineer)
137 | 3.22 | 2 | ACID WASH | B-Wing | Task | 120 | 2028-04-22 | 2028-09-08 | 2028-07-31 | 2028-12-16 |  |  | 0% | 124SS+427d | Vicky Satpute (Sr. Engineer)
138 | 3.23 | 2 | TILE GROUTING | B-Wing | Task | 100 | 2028-05-22 | 2028-09-14 | 2028-08-31 | 2028-12-25 |  |  | 0% | 137SS+31d | Vicky Satpute (Sr. Engineer)
139 | 3.24 | 2 | SNAGGING & DESNAGGING | B-Wing | Task | 40 | 2028-09-22 | 2028-11-07 | 2028-11-15 | 2028-12-30 |  |  | 0% | 129SS+412d | Vicky Satpute (Sr. Engineer)
140 | 3.25 | 2 | DEEP CLEANING | B-Wing | Task | 60 | 2028-09-22 | 2028-11-30 | 2028-10-23 | 2028-12-30 |  |  | 0% | 136SS | Vicky Satpute (Sr. Engineer)
141 | 3.26 | 2 | ELEVATION FEATURES | B-Wing | Task | 165 | 2028-04-22 | 2028-10-31 | 2028-06-22 | 2028-12-30 |  |  | 0% | 121SS+358d | Vicky Satpute (Sr. Engineer)
142 | 3.27 | 2 | OTHER SERVICE | B-Wing | Task | 15 | 2028-10-23 | 2028-11-08 | 2028-12-30 | 2029-01-16 |  |  | 0% | 139SS+45d | Vicky Satpute (Sr. Engineer)
143 | 3.28 | 2 | NOC'S | B-Wing | Task | 44 | 2028-08-22 | 2028-10-11 | 2028-11-30 | 2029-01-19 |  |  | 0% | 139SS+15d | Vicky Satpute (Sr. Engineer)
144 | 4 | 1 | EXTERNAL DEVELOPMENT WORK & SERVICES INCLUDING UTILITIES | External Development | Summary | 861.5 | 2026-04-01 | 2028-10-17 | 2026-03-19 | 2029-01-30 | 2026-03-19 |  | 4% |  | To be appointed (Jan-27)
145 | 4.1 | 2 | UGWT | External Development | Summary | 681.5 | 2026-04-01 | 2028-03-21 | 2026-03-19 | 2028-06-28 | 2026-03-19 |  | 27% |  | To be appointed (Jan-27)
146 | 4.1.1 | 3 | CIVIL WORKS | External Development | Task | 90 | 2026-04-01 | 2026-07-14 | 2026-03-19 | 2026-07-01 | 2026-03-19 |  | 65% | 2SS+261d | To be appointed (Jan-27)
147 | 4.1.2 | 3 | ELECTRO- MECHANICAL WORKS | External Development | Task | 100 | 2027-10-22 | 2028-02-15 | 2028-01-31 | 2028-05-25 |  |  | 0% | 146FS+578d | To be appointed (Jan-27)
148 | 4.1.3 | 3 | TESTING& COMMISSIONING | External Development | Task | 25 | 2028-02-22 | 2028-03-21 | 2028-05-31 | 2028-06-28 |  |  | 0% | 147FS+5d | To be appointed (Jan-27)
149 | 4.2 | 2 | STP | External Development | Task | 545 | 2026-09-22 | 2028-06-17 | 2026-11-30 | 2028-08-25 |  |  | 0% | 146SS+256d | To be appointed (Jan-27)
150 | 4.3 | 2 | COMPOUND WALL | External Development | Task | 250 | 2027-07-22 | 2028-05-08 | 2027-09-30 | 2028-07-17 |  |  | 0% | 149SS+304d | To be appointed (Jan-27)
151 | 4.4 | 2 | AMENITIES (Civil + Hardscape + Softscape) (Ground+Podium ) | External Development | Task | 180 | 2028-03-22 | 2028-10-17 | 2028-04-29 | 2028-11-24 |  |  | 0% | 150SS+212d | To be appointed (Jan-27)
152 | 4.5 | 2 | PLUMBING & SEWERAGE WORKS | External Development | Task | 200 | 2028-01-22 | 2028-09-11 | 2028-05-31 | 2029-01-18 |  |  | 0% | 151SS+32d | To be appointed (Jan-27)
153 | 4.6 | 2 | TRANSFORMER ROOM/ SUB STATION/ EXTERNAL ELECTRICAL WORK | External Development | Task | 210 | 2028-01-22 | 2028-09-22 | 2028-05-31 | 2029-01-30 |  |  | 0% | 152SS | To be appointed (Jan-27)
154 | 4.7 | 2 | ENTRANCE GATE WITH SECURITY CABIN & ENTRY GATE - 2 Nos | External Development | Task | 120 | 2028-05-15 | 2028-09-30 | 2028-07-31 | 2028-12-16 |  |  | 0% | 153SS+61d | To be appointed (Jan-27)